## estitmates and what they mean (hidden)
[7 empty] | dev total | qa total | total
[7 empty] | 167 | 269 | 436
[7 empty] | 38% | 62%
Iteration | id | story | estimate | started | delivered | accepted | Dev time | QA time | Total | comment
#REF! |  |  |  | 2014-01-22 | 2014-01-24 | 2014-01-24 | 2 | 0 | 2
|  |  |  | 2014-01-29 | 2014-02-04 | 2014-02-04 | 6 | 0 | 6 | Akshay addded all the detail of this story AFTER it was sized
|  |  |  | 2014-01-28 | 2014-01-29 | 2014-01-30 | 1 | 1 | 2
|  |  |  | 2014-01-22 | 2014-01-29 | 2014-02-04 | 7 | 6 | 13 | Chris changed the estimate after starting the work
|  |  |  | 2014-01-29 | 2014-02-04 | 2014-02-04 | 6 | 0 | 6
|  |  |  | 2014-02-04 | 2014-02-05 | 2014-02-25 | 1 | 20 | 21
|  |  |  | 2014-02-06 | 2014-02-19 | 2014-02-19 | 13 | 0 | 13
|  |  |  | 2014-02-08 | 2014-02-12 | 2014-02-19 | 4 | 7 | 11
|  |  |  | 2014-02-17 | 2014-02-17 | 2014-02-19 | 0 | 2 | 2
|  |  |  | 2014-02-25 | 2014-02-27 | 2014-02-27 | 2 | 0 | 2
|  |  |  | 2014-02-27 | 2014-02-27 | 2014-02-27 | 0 | 0 | 0
|  |  |  | 2014-03-07 | 2014-03-12 | 2014-03-21 | 5 | 9 | 14 | ashkay added scope to story after it was delivered
|  |  |  | 2014-02-19 | 2014-02-25 | 2014-03-12 | 6 | 15 | 21 | ashkay added scope after story was sized and started
|  |  |  | 2014-03-11 | 2014-03-12 | 2014-03-21 | 1 | 9 | 10 | ashkay added scope after story was delivered
|  |  |  | 2014-03-13 | 2014-03-14 | 2014-03-20 | 1 | 6 | 7 | was resized from 4 to 1 AFTER it was finished, scope was changed after it was delivered
|  |  |  | 2014-03-14 | 2014-03-18 | 2014-03-25 | 4 | 7 | 11 | scope was added after sizing. was resized after starting. story was changed after it was delivered
|  |  |  | 2014-03-20 | 2014-03-24 | 2014-03-26 | 4 | 2 | 6 | lots of movement
|  |  |  | 2014-03-13 | 2014-03-21 | 2014-03-31 | 8 | 10 | 18 | scope changed after started
|  |  |  | 2014-03-13 | 2014-03-21 | 2014-04-01 | 8 | 11 | 19 | so much movement - resized after starting (4 to 8). stopped. started etc
|  |  |  | 2014-04-01 | 2014-04-04 | 2014-04-08 | 3 | 4 | 7 | scope added after sized. scope added after started
|  |  |  | 2014-03-21 | 2014-03-25 | 2014-03-31 | 4 | 6 | 10 | shall i keep writing the same thing over and over?
|  |  |  | 2014-04-01 | 2014-04-01 | 2014-04-01 | 0 | 0 | 0
|  |  |  | 2014-03-28 | 2014-04-08 | 2014-04-15 | 11 | 7 | 18 | shall i keep writing the same thing over and over?
|  |  |  | 2014-04-24 | 2014-04-25 | 2014-04-25 | 1 | 0 | 1
|  |  |  | 2014-03-21 | 2014-04-01 | 2014-04-15 | 11 | 14 | 25
|  |  |  | 2014-04-07 | 2014-04-08 | 2014-04-16 | 1 | 8 | 9
|  |  |  | 2014-04-09 | 2014-04-09 | 2014-04-15 | 0 | 6 | 6
|  |  |  | 2014-04-07 | 2014-04-08 | 2014-04-15 | 1 | 7 | 8
|  |  |  | 2014-04-15 | 2014-04-22 | 2014-04-28 | 7 | 6 | 13
|  |  |  | 2014-04-17 | 2014-04-24 | 2014-04-25 | 7 | 1 | 8
|  |  |  | 2014-04-11 | 2014-04-14 | 2014-04-16 | 3 | 2 | 5
|  |  |  | 2014-04-11 | 2014-04-14 | 2014-04-22 | 3 | 8 | 11
|  |  |  | 2014-04-11 | 2014-04-11 | 2014-04-22 | 0 | 11 | 11
|  |  |  | 2014-04-02 | 2014-04-08 | 2014-04-15 | 6 | 7 | 13
|  |  |  | 2014-04-09 | 2014-04-15 | 2014-04-25 | 6 | 10 | 16
|  |  |  | 2014-04-23 | 2014-04-23 | 2014-04-25 | 0 | 2 | 2
|  |  |  | 2014-04-24 | 2014-04-24 | 2014-04-25 | 0 | 1 | 1
|  |  |  | 2014-04-24 | 2014-04-24 | 2014-04-25 | 0 | 1 | 1
|  |  |  | 2014-04-24 | 2014-04-25 | 2014-04-25 | 1 | 0 | 1
|  |  |  | 2014-04-11 | 2014-04-11 | 2014-04-15 | 0 | 4 | 4
|  |  |  | 2014-04-25 | 2014-04-25 | 2014-04-28 | 0 | 3 | 3
|  |  |  | 2014-04-16 | 2014-04-22 | 2014-04-30 | 6 | 8 | 14
[7 empty] | 0 | 0 | 0 | not progressed through workflow
|  |  |  | 2014-04-30 | 2014-04-30 | 2014-05-21 | 0 | 21 | 21 | devs not using workflow
|  |  |  | 2014-05-08 | 2014-05-20 | 2014-05-30 | 12 | 10 | 22
|  |  |  | 2014-05-07 | 2014-05-12 | 2014-05-29 | 5 | 17 | 22
|  |  |  | 2014-05-21 | 2014-05-21 | 2014-05-21 | 0 | 0 | 0

## estimates report (hidden)
story point | time taken
2 | 2
5 | 6
5 | 2
5 | 13
5 | 6
1 | 21
5 | 13
8 | 11
5 | 2
2 | 2
5 | 0
2 | 14
2 | 21
2 | 10
1 | 7
2 | 11
1 | 6
1 | 18
8 | 19
1 | 7
2 | 10
1 | 0
2 | 18
1 | 1
5 | 25
2 | 9
1 | 6
2 | 8
2 | 13
2 | 8
1 | 5
1 | 11
2 | 11
2 | 13
5 | 16
1 | 2
1 | 1
1 | 1
1 | 1
2 | 4
1 | 3
2 | 14

## my report (hidden)
alpha
story points | average days taken | story points | variation |  | delivered | taking | using
|  |  |  | sprint 1 - 7 | 106 story points | 104 days | 371 person days

## epic report (hidden)
type | label | story | Count | Points
#REF!

## data for burndown
starts | total | sprint | to do | done | velocity (avg) | trend
2014-06-01 | 50 | 1 | 50 | 0
15-Jun-2014 | 50 | 2 | 46 | 4 | 2
29-Jun-2014 | 50 | 3 | 43 | 7 | 4 | 42
13-Jul-2014 |  | 4 |  |  |  | 39
27-Jul-2014 |  | 5 |  |  |  | 36
10-Aug-2014 |  | 6 |  |  |  | 32
24-Aug-2014 |  | 7 |  |  |  | 29
7-Sep-2014 |  | 8 |  |  |  | 25
21-Sep-2014 |  | 9 |  |  |  | 22
5-Oct-2014 |  | 10 |  |  |  | 18
19-Oct-2014 |  | 11 |  |  |  | 15
2-Nov-2014 |  | 12 |  |  |  | 11
16-Nov-2014 |  | 13 |  |  |  | 8
30-Nov-2014 |  | 14 |  |  |  | 4
14-Dec-2014 |  | 15 |  |  |  | 1
28-Dec-2014 |  | 16 |  |  |  | -3

## zendesk (hidden)
requested by | lable | id | story
#REF!

## printable cards (hidden)
type | id | story
#REF!

## backlog (hidden)
Iteration | Area | Feature | Type
#REF!

## added mid sprint (hidden)
Iteration | Start | Created | 15
#REF!
*
*
*
*
*
*
*
*
*
*
*
*
*
*
*

## in progress, by owner (hidden)
Iteration | Owner | Story | Type
#REF!

## done by type pvt (hidden)
Iteration | Type | Done
#REF!

## done by Labels pvt (hidden)
Iteration
#REF!

## sprint dashboard (hidden)
Sprint Ends | 2014-03-18
Percentage Done | #DIV/0!
Time Burnt | 1130.77%
Status | #DIV/0!
Done |  |  | Due / In Progress
Area | Type | Feature | Area | Type | Feature
#REF! |  |  | #REF!

## pressure gauge
some time stuff...
the question | title | the answer
When did we start? | Start | 2014-06-01
When are we finishing? | End | 2014-12-28
So how many days in the plan? | Duration | 150
What day is it today? | Today | 30 Jul 2014
So the number of days that remain is... | Remaining | 108
some work stuff...
How many things to do are there? | Total | 100
How many have we done? | Done | 15
So how many left to do | Remaining | 85
some maths...
% of time still left | % time left | 72
% of work still remaining to be done | % work left | 85
finally, some witchcraft (or trend calculations)...
days burnt | days burnt | 43
work delivered | points completed | 15
so velocity per day | velocity (per day) | 0.3
so how many days needed to complete the remaining work? | days required | 244
so if i add 244 days to today i get... | calculated end date | 6 Jul 2015
so whats the overall status based on velocity... | RAG | oh dear..
Formulas:
the answer = NETWORKDAYS(D3,[the answer, row above])
the answer = NETWORKDAYS([the answer, row above],D4)

## done by team pvt (hidden)
Iteration
#REF!

## team capacity (hidden)
Name | Possible | Actual | Allocated to sprint | so days available
Alex Tomlins | 10 | 9 | 100% | 9
Daniel Roseman | 10 | 4 | 100% | 4
David Thompson | 10 | 7 | 100% | 7
Jake Benilov | 0 | 0 | 0 | 0
Paul Hayes | 10 | 10 | 20% | 2
Stuart Gale | 10 | 9 | 100% | 9
Tekin Suleyman | 10 | 8 | 100% | 8
Vinay Patel | 10 | 0 | 100% | 0
| 70 |  |  | 39
|  | So team strength as %: |  | 56%