## Copy of Service Design Activity Planning
What do we need to do? | Journey mapping | User research | Who will do this? | How will this get done? | What resources do we need? | What support would you like from GDS? | How could LA collaboration help? | What dependencies does this have? | How long will this take?
Hypothetical As-is journey mapping | Hypothetical as-is mapping
Plan research (GDS research training day to kick off) |  | As-is journey and user research
Recruit target users for discovery phase research (as-is journey mapping and user needs)
Conduct research | Research informed as-is journey mapping
Analyse research & prepare to share with GDS and collaborating LAs
Workshop with GDS to map 1st iteration of new service design integrating Verify (overlaying process and tech in user journey) | To-be journey mapping and itteration
Map assisted digital and offline user journeys (different councils lead on different use cases, and then share findings)
GDS develop a common service design pattern after the 1st iteration service design workshop, and share it with the LAs.
Comment on the common pattern developed by GDS (based on continued user research and assisted digital/offline journey development)
Develop approach for implementing service design to pitch to design team/board for approval to proceed to build (must include a process description and technical plan) |  | User research to test out ideas
Prepare user research findings for publication and sharing with other LAs
Approve 1st iteration of the service design pattern by GDS for publication
GDS prepare common high level user journeys and service pattern for publication
Map out detailed local iteration user journey/s (ideally aligning across councils)
LA collaborators review common high level user journeys and service pattern for GDS to publish
Submit local service design plan (linked to tech set-up) for gate review

## Copy of Tech Acitivities Planning
What do LAs need to do? | Steps | Who will do this? | How will this get done (meetings, events, outsourcing)? | What resources do we need? | How can GDS help? | How can LA collaboration help? | What dependencies does this have? | How long will this take?
MITIGATING FRAUD
Share existing fraud incident reporting procedures
Analyse 1st service design for fraud, cyber and internal data-breach threats
SECURITY
Gather evidence to demonstrate that this transformation project is within the scope of your council's Information Security Management System (ISMS) - e.g. IS027001. Include Certification type and scope | Outline the scope of the ISMS, highlgiht any areas of your business that are not included, and what issues and risks it considers.
Analyse how you'll use personal data in this transformation project and check that your plan is within the scope of the certification or information security procedures you have in place.
If the project outside scope of your ISMS then you'll need to provide evidence of how you'll mitigate risks introduced
Outline what risks you have accepted and why
Get your Information Security Officer/ Head of Audit/ SIRO's sign off on the information security strategy you're submitting to GDS
TECHNICAL DESIGN
1st iteration service technical architecture, highlighting data flows
Prepare technical resourcing plan for sharing with GDS, outling how you'll deliver the target archtiecture, and your biggest resource gaps or support needs (e.g. which systems do you own, what do you need to buy, etc) | Clarify whether you need to match records and work out how you're going to do it if so (with what data). Presume for this exercise you'll need to match against your council tax records.
Identify your data sources and software components required for 1st iteration technical architecture (e.g. what data would you use to evidence eligibility)
Identify what you own and what do you need to buy in
Understand what skills you have and need to build, buy, and manage the system
OPERATIONAL SUPPORT
Plan monitoring and alerting procedures for 24/7 service
Identify who will respond to technical issues (is it business critical to have site live 24/7?)

## Copy of Perfromance Monitoring
Purpose Why is the service/tool/thing being built?
Goals What are the goals of the service/tool/thing? How will things be better because of it?
User Story as a [user] - I need to [do something] - so that [I can achieve my goal]
How will we meet the user needs and goals? Set some hypotheses on how we could fulfill the user need [in a perfect world with infinite resources] By [doing something] we can meet this user need and meet this goal
KPIs Define what you want to measure KPI to measure if a user need or goal is being met KPI can be a measure derived from - Existing data - A best guess that can be iterated on once you have reliable data | p
Other measures or targets Define what you want to measure Additional non KPI measures to determine if a user need or goal is being met May feed into the KPI May be a dataset that helps to improve the service