## Sheet1
5 |  |  |  | High = 5; Medium = 3; Low = 1 | [11 empty] | Other factors considered in prioiritisation
Presentation Cluster/group | Cluster number | Epic | Who | MVC Priority (relieves councils biggest pains) | DCLG priority (enables widespread standards adoption) | Enablement priority rank (supports top MVC priority/ widespread standards adoption) | Overall score | Evidence/Justification | Users/Personas | Possible deliverables | Ultimate outcomes (Benefits and savings) | Stories | Dependencies | Risks | Issues / notes | Resources available | Cost to develop/ input required (e.g dev days) | Level of cost to implement to council | Level of tech feasibility | Level of Dependency/ risk
Business | 0 | Common metrics / KPIs and benchmarks (could be Measuring impact) | Linda | 3 | 5 | 5 | 13 | How will this project measure it's impact? What are the KPIs? What are the before and after benchmarks? If we don't have these, how can we make a business case/help others to make a case? How can central gov policy-makers and councils (i.e. budget-holders) get a sense of how well they're doing relative to each other on service improvement and channel shift? | waste manager, digital leader, DCLG, supplier business manager | Propose & debate likely KPIs around prioritised services/transactions e.g. cost per transaction (new bin), cost per transaction (missed bin), digital uptake. |  |  | Councils and suppliers sharing their performance data with this project. | No standardised data enabling us to compare apples with apples...
[10 empty] | Agree "minimum viable KPIs" for use in project documents and business case deliverables. | A national view of the relative efficiency of waste services? Not sure this will appeal to councils?! |  | APIs created by project supporting this work (to ensure some automated data)
[10 empty] | Find and collate any real or extrapolated data that can be used to populate the KPIs for the project and for business cases | Real data to inform local business cases, enabling wider uptake of the standard, and potentially making the case for other standards too.
Business | 0 | Supporting local authority business cases | Linda | 5 | 5 | 5 | 15 | Individual councils need to make the case for investment in the use of any standards, internally and to their members. | waste manager, digital leader, transformation manager | Collated/documented evidence based on the experience and data of the MVC - e.g. the costs of not following a standard, the benefits and savings of doing so, the steps needed to implement various aspects, the cost/effort associated with these. | Real data to inform local business cases, enabling wider uptake of the standard, and potentially making the case for other standards too. |  | Participating local authorities need to share/be transparent about their data. Agreeing benchmarks/ KPIs | Limited access to real savings data over course of the project | Potentially higher impact/ value product to sector if achieveable
A template/model that LAs could use to plug in their local data.
Business | 0 | Supporting central business cases | Linda | 5 | 5 | 5 | 15 | DCLG or other central bodies may want to look for opportunities for central investment/incentives that support all LAs in improving waste services - perhaps providing a model for other local service areas. | DCLG, policy makers | Extrapolated evidence of potential benefits of central funding/coordination etc. Could also potentailly discuss/suggest particular models/approaches. | Increased investment in the development of more effective waste services (and potentially other services/standards too) |  | DCLG Waste Policy and Local Digital Programme DD seeing value RE SR
Business | 0 | Supporting supplier business cases | Linda | 3 | 3 | 3 | 9 | Suppliers may need to make the case internally to adopt a standard - what can this project do to support that? (Not sure they asked for this, so it's an outlier) | Supplier business manager (including LAs who sell services to neighbours) | Evidence for adopting data standards and perhaps using a shared addressing service (in medium term) for particular waste services | Increased take up of the standard by suppliers | Violia story kind of caputured in Helen M's private sector discussion notes. | Getting more suppliers signed up than we currently have. | Suppliers not forthcoming with cost data. | We have some good time estimates from Violia that we could follow up with and Methods would likely have some good data. Might need to commission this as secondary priority and kill if it's taking too much resource. | Spencer from Liveperson.
Business? | 0 | Agreeing the afterlife of the standard | Linda | 5 | 5 | 5 | 15 | This project is only funded until Dec 2015. What will happen to the standard after this? Who will maintain and promote it? What models might work? We need to be able to make a recommendation, ideally based on consultation. | waste manager, supplier business manager, DCLG | Propose & debate possible scenarios. Document the pros & cons of each. Agree the proposal to take forward. | Standards around waste services continue to be supported and developed |  | Flag in next steps: IEG4 benfits model; WRAP hosting and governance.
Missed collections | 1 | Managing "missed" collections | Sarah | 5 | 5 | 5 | 15 | High source of issues for customer services. Citizens claim that their waste hasn't been collected, customer services need to establish if this is true, if so, why. Some use of real time reporting from cabs, but not universal. Also involves scheduling the collection of any that are deemed to be genuinely missed. | citizen customer services waste operative, waste manager | Collection issues via API for Customer services and/or citizens | Customer service staff could have real time access to data from the kerbside, helping them to resolve citizen queries/complaints more efficiently. Service Managers would have a more accurate picture of the quality of the collection service (e.g. how many genuine "misses"? Why? How many are due to citizen behaviour? How might this be addressed?) Potentially some of this data could also be exposed to citizens e.g. has the truck already been down my street? (Note: there was a lot of resistence to sharing this kind of data publically, in case it increased calls and/or people cutting things too fine) |  | Collection days (if assume collection data needed) Real-time reporting.
An issue types taxonomy
Regular collections | 2 | Understanding what goes where | Paul | 1 | 3 | 1 | 5 | Ongoing source of confusion for citizens. Different terminology used in various places. May contribute to low recycling rates and/or accidental "contamination" of recycling. | citizen customer services waste operative waste manager | Recommended terminology. Taxonomies of items (see Open Resources). | Could use this to offer a more dynamic experience for citizens - e.g. a web page or app which reliably informs the user of the disposal options for any item of waste. This needn't just include council funded disposal options, but could also link to local re-use charities etc. This could be developed locally (i.e. for just one council) or a 3rd party could build a tool that should the answers for any address in the UK (ambitious!). |  |  |  |  | Alex Coley team at Defra?
Collections model that links collections and items. Things that enable LAs to make the experience on their sites more intuitive and dynamic? Perhaps a demo of this in action?
Regular collections | 3 | Collection day information | Paul | 1 | 3 | 3 | 7 | One of highest used services. Particularly around bank holidays/other disruptions. Opportunity to open up data to more formats and ways to access / make it more dynamic and convenient. | citizen customer services waste operative | API for querying collections by UPRN that includes full collection information. | Coucils could use this to offer a more dynamic experience for citizens - e.g. a web page which is always up to date and where they can easily find information for any address. The same data could also be used to power reminder/alert services e.g. SMS, emails, app push notifications. |  | Address API, business rules around bank holidays? | Potential overlap/ conflict with medium term DCLG addressing service project? | Ensure join-up with DCLG Local Addressing standards work
Processing payment & discounts | 4 | Ordering and managing containers | Paul | 1 | 1 | 1 | 3 | Manging the ordering/payment for containers .Plus managing the abuse of this: Boxes and bins cost the council money to buy and to distribute. Some anecdotal evidence that people are abusing this. Is it worth tracking the number of orders per household? | customer services, waste manager, | Workshop with those working on DWP data-querying to see if they could allow CS teams to verifying if discount applications were legitimate | Reduced wastage, as containers will only be sent to proprties that need them. More detailed information on the bin status and changes at each property. |  |  |  | Could a system help to record these details? Should it be separate or part of council's CRM system?
Processing payment & discounts | 4 | Managing payments | Sarah | 5 | 1 | 5 | 11 | Common pain point around timely/efficient payment reconciliation and linking up internal systems around ordering/paying/scheduling delivery. e.g. currently might have a time lag between a bin being ordered and it being sent out, because payment has to clear various hoops. | customer services, waste manager, waste operative | Workshop with payment suppliers | Improved citizen experience, with fewer time lags? Less time spent on payment processing internally. |  | Payment system providers?
Processing payment & discounts | 4 | Checking eligibility for discounts | Linda | 1 | 1 | 1 | 3 | Verifying whether someone is eligible for a free or discounted service. |  | Workshop with those involved in benefits provision. | Reduction in revenue lost through fraud. Potentially a simpler experience for all citizens as eligibiliy will be swiftly checked and only when needed. |  |  |  | Connection with AX project - ie noting all places where better data sharing/ querying could reduce processing time and abuse of LG services.
Modifying collections | 5 | Managing assisted collections (and other flags) | Paul | 1 | 1 | 3 | 5 | Some (all?) councils offer assisted collections. Where is the record of which households need this? How is it maintained? (This could be extended to include other types of flag for a household e.g. frequently complains, refrequently contaminates/fails to present, plus maybe the location of the bins if not obvious?) | customer services, waste manager, waste operative | Model and API to include support for assisted collections. | Refuse collectors have more accurate and up to date information about the specifc needs of residents, reducing friction and complaints? |  |  |  | Could a system help to record these details? Should it be separate or part of council's CRM system?
Modifying collections | 5 | Adding a new address to the round | Paul | 1 | 1 | 3 | 5 | Some best practice around use of Gazetter... but sounds as if this is not as dynamic or universal as it could be? However, this is low frequency in most places, partiuclarly compared to the daily costs of collections etc | customer services, waste manager, waste operative | Common Addresses API. |  |  |  |  | Wouldnt the standards part of this be supported by Address API (21)?
Gazetteer best practce.
Modifying collections | 5 | Booking and managing special regular collections e.g. garden waste | Paul | 1 | 1 | 3 | 5 |  |  | Model and API to include support for special collections.
Contracts | 6 | Simplifying tendering and contracts | Linda | 5 | 3 | 5 | 13 | Came up as a pain point from all sides! Reduce council time to put together a tender. Reduce contractor time to adapt their proposals to each council. Reduce contractor time to implement adaptations. Reduce number of tender errors/ inclarity of ask, which leads to unforeseen costs on both sides. | waste manager, supplier, business manager customer services | A set of guidelines for tendering: e.g. Data format definitions for required datasets; Template paragraphs/tables to add to briefs/contracts; Checklist/ menu of best practise contract ingredients. Perhaps tips/best practice on how to clean up your data | Reduced time to prepare tenders. Reduced time for suppliers to implement service setup with council data. |  |  | Might increase council work to adapt their data to needed formats. Who would maintain/ update checklists
Bulky waste | 7 | Managing bulky waste collections | Paul | 1 | 3 | 1 | 5 | It's crucial that the customer accurately describes the bulky waste so that the right size of vehicle can be scheduled to collect it. Currently there is no standard way of capturing this. There are costs associated with failed collections e.g. truck is sent out but can't fit the load in | citizen customer services waste operative waste manager | Standard list of terms (see "What goes where") Recommend a Standard or best practice approach to describing bulky waste items? | Councils could offer a more intuitive (and standardised) experience to citizens booking a bulky waste collection, similar to the use of "golf ball, dinner plate, dustbin lid" for pothole reporting.
Information flow | 8 | Reporting to Defra | Sarah | 5 | 1 | 5 | 11 | Can take from 2 days to 2 weeks for each submission to WasteDataFlow. Effort/cost to councils (anecdotal, but no hard numbers yet) | waste manager | Weighbridge data standard? APIs rather than spreadsheets? | Less time spent on reporting - greater automation. Better understanding of the impact and cost of central reporting reqiurements on local authorities. |  |  | WasteDataFlow is centrally managed. Might be hard to get traction. | Needs more research as to what would be useful and how it fits into the picture.
Discovery workshop with Defra/ WRAP and EA to uncover better standards
Information flow | 8 | Using data to encourage behaviour change | Sarah | 5 | 1 | 5 | 11 | Citizens are 32% more likely recycle if they have better information about what is done with it. Possible opportunity to use data to encourage behaviour change, | citizen? waste manager? Defra? EA? 3rd sector/ environmental lobby | Statistics definition for different resource flows. Explore data model and API extensions to include this data. | Data could be visualised in compelling and competitive ways to stimulate behaviour change |  |  |  | Needs more research
Information flow | 8 | Visualising & managing the waste ecosystem | Sarah | 5 | 1 | 5 | 11 | Anecdotal evidence that there is cause and effect in the waste system e.g. starting charging for bulky waste collection and flytipping goes up. Contractors are rewarded on speed of round, litter and street cleansing goes up. Reduce bin size and recycling contamination goes up. Also anecdotal evidence of members insisting on changes to one part of the systems without realising impact elsewhere. How might waste managers build up a more complete picture of waste related behaviour? | waste manager | A case study (or mock up?) of a dashboard of waste related behaviour by street? | Could enable service managers to pilot new schemes and make recommendations to members based on data. PLUS this could help the service managers better coordinate the services they offer/schedule (as suggested by Brentwood)
Fly tipping | 9 | Managing fly tipping | Sarah | 5 | 3 | 3 | 11 | Various different apps and methods of reporting. Rarely linked full-circle. Anecdotal evidence that 3rd party apps are generating extra handling work in spite of their good intentions. | citizen customer services waste operative waste manager | Data format for incident reporting. Standard location identifiers? Link up to land registry re. who owns the land? | More efficient handling of fly tipping reports. Better collaboration with civic tech makers |  | Creation of land reg API at land reg side? don't think register is digital yet | Land reg programme deprioritises this work
Hack day
|  | Collections data model | [5 empty] | Base for subsequent information services and contracts. |  | Core data model documentation. |  |  |  |  | Is this worth highlighting as a separate epic?
|  | Address look-up/management | [5 empty] | As a common component, many other systems query addresses, sometimes in real-time. A standard API could help reduce data duplication. | digital team | Address query API |  |  |  | In-cab need copy of data anyway so value is less. Also data format already well established.